## Help
INSTRUCTIONS FOR USE
C A U T I O N S
1. | Don't Delete or Insert any Row or Columns.
2. | Plotting interval must be entered before constructing the bars.
3. | Don't change plotting interval after constructing bars without reconstructing bars.
Data Entry
Before starting data entry on a new project:
a. Unhide all rows & columns by pressing [CTRL-A] then right click in Column heading & click Unhide,
then right click on Row heading & click Unhide.
b. Clear all bars by selecting cells H5:GY104 and pressing [Del] key.
Data may be entered only in the following cells:
1. | A2 (Project Name) Required Entry
2. | A3 (Spec No.) Required Entry
3. | F3 (Plotting Interval) Required Entry. Bars must be reconstructed if plotting interval is changed.
Plotting interval will determine how many sheets will be required to print BarChart.
Each printed page will have about 44 rows in addition to header.
If no columns are hidden, first page will have about 28 columns of bars.
If columns C, D, E & F are hidden, first page will have about 44 columns of bars.
In both cases subsequent pages will have 44 columns of bars.
4. | A5:C104 (Item #s, Tasks & Costs) Required Entries for rows with tasks.
5. | H4 Enter earliest date as mm/dd/yy. All other dates in Row 4 computed by formula. Required Entry
6. | H5:FA104 (1 to cause Red bar, [Del] clears the Red bar) Required Entries to make bars.
Note: | Dates do not display year. Odd numbered year dates are black, even red.
Constructing Bars
There are three methods of constructing and modifying bars:
1. | Entering a "1" in a cell causes it to be filled with Red. [Del] on a cell clears the Red fill.
2. | Copy all or part of an existing bar and paste in a new location.
Copy all or part of an existing clear area in H5:FA104 and paste over Red fill to clear it.
3. | Drag the lower right corner of a cell containing a bar horizontally to desired length.
To use this method, menu "Tools, Options, Edit, Allow cell drag and drop" must be checked on.
Drag is enabled if there is a small square in the lower right corner of any selected cell.
Printing
1. | Before printing
a. Select entire rows with "H" in Green Fill in Col G & FB, then right click Row heading & click Hide.
b. Select entire columns with "H" in Green Fill in Row 1, then right click Column heading & click Hide.
c. May also select entire columns C and/or D, E & F, then right click Column heading & click Hide.
2. | Preview BarChart sheet. If OK, print it.
Programmer's Information
This information is not needed by workbook users!
There are no active macros in this workbook.
Formulas on BarChart sheet:
H4 | =H4+Intv
(H4 copied to I4:GY4)
D5 | =IF(F5<>"",HLOOKUP(MATCH(1,H5:GY5,-1),$H$3:$GY$4,2),"")
(D5 copied to D6:D104)
E5 | =IF(F5<>"",HLOOKUP(MATCH(2,H5:GY5,1),$H$3:$GY$4,2),"")
(E5 copied to E6:E104)
F5 | =IF(SUM(H5:GY5)>0,SUM(H5:GY5),"")
(F5 copied to F6:F104)
Note: Columns D, E & F appear blank if there are no red bars in the row.
F4 | ="No. of "&Intv&" Day Periods in Bar"
I4 | =H4+Intv
(I4 copied to J4:GY4)
HC5 | =IF($C5<>0,SUM(INDIRECT(ADDRESS(CELL("row",$H5),8) & ":" & ADDRESS(CELL("row",$H5),HC$4)))/$F5*$C5,"")
(HC5 copied to HC5:HZ104)
IA5 | =IF(C5<>"",C5,"")
(IA5 copied to IA5:IA104)
HB2 | =ROUND(Days*HB3,0)+Date1
(HA1 copied to HB1:IA1)
HC4 | =ROUND(Days*HC3/Intv,0)+7
(HC4 copied to HD4:IA4)
IE3 | =ProjectName&" - "&SpecNo
C105 | =SUM(C5:C104)
D105 | =MIN(D5:D104)
E105 | =MAX(D5:D104)
F105 | =ROUND((E105-D105+1)/Intv,0)
HC105 | =SUM(HB5:HB104)/Total
(HC105 copied to HD105:IA105)
Formatting on BarChart sheet:
Format of H5:GY104
Single line all around, Pattern solid, No fill, Font color white, Not locked, Not hidden
Conditional format of H5:GY104
If cell value is equal to 1: Font color is Red, Pattern solid, Fill color Red
Conditional format of G9 & GZ9 (G9 copied to G9:G104 and GZ9 copied to GZ9:GZ104)
Formula =AND($B9="",$F9=""), Font color auto, Pattern Solid, Fill color green,
Cells contain an "H" formatted white.
Conditional format of I9 (I9 copied to I9:GY1)
Formula =SUM(I$5:$GY$104)=0, Font color auto, Pattern Solid, Fill color green,
Cells contain an "H" formatted white.
Data Validation of H5:GY104
Allow List, Source 1, Ignore Blank
Each cell with a "1" will have a Red fill and will add to sum in the "Periods Worked" column (Col F).
Data Validation of F3
Allow List, Source 1, 2, 4, 5, 7, 10, 14, Ignore Blank check mark cleared, InCell Dropdown checked on.
Title: Plotting Interval, Input message: "Must be set before constructing bars!"
1, 2, 4, 5, 7, 10 or 14 Days.
Data Validation of all cells with formulas or static valuesto prevent overwriting the formulas
Allow Custom, Formula: ="", Ignore Blank check mark cleared.
Error Title: Formula, Error message: "Do not overwrite formula!"
Cell G5:G16 are merged. Cells GZ5:GZ13 are merged
CostTimeChart sheet formulas:
CostTime series:
X | =BarChart!$HB$3:$IA$3
Y | =BarChart!$HB$105:$IB$105
Goal Series:
X | =BarChart!$ID$5:$ID$7
Y | =BarChart!$IE$5:$IE$7
Chart Title: =ConstrScheduleDrag.xlt!ChTitle

## BarChart
See instructions on Help sheet.. Plotting interval must be set before constructing bars. | [5 empty] | Beg |  | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | H | End |  | 2005-10-18 | 2005-10-23 | 2005-10-29 | 2005-11-03 | 2005-11-08 | 2005-11-14 | 2005-11-19 | 2005-11-24 | 2005-11-30 | 2005-12-05 | 2005-12-10 | 2005-12-16 | 2005-12-21 | 2005-12-26 | 2005-12-31 | 2006-01-06 | 2006-01-11 | 2006-01-16 | 2006-01-22 | 2006-01-27 | 2006-02-01 | 2006-02-07 | 2006-02-12 | 2006-02-17 | 2006-02-23 | 2006-02-28 | Red Line |  | Drag
Maintenance Building #3 |  |  | Odd # Years Black, Even #s Red | [191 empty] | 0% | 0% | FALSE
XX06-99 |  |  | Plotting Interval in Calendar Days |  | 4 | Beginning of Contract Time . | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | End of Contract Time . |  | 0% | 4% | 8% | 12% | 16% | 20% | 24% | 28% | 32% | 36% | 40% | 44% | 48% | 52% | 56% | 60% | 64% | 68% | 72% | 76% | 80% | 84% | 88% | 92% | 96% | 1 | 20% | 0% | ChTitle | Maintenance Building #3 - XX06-99
Task No. | Tasks | Cost of Task | Plan Start of Task | Plan Finish of Task | No. of Days in Bar | [162 empty] | Formulas only to right. No User entry! | 8 | 8 | 10 | 11 | 12 | 14 | 15 | 16 | 18 | 19 | 20 | 22 | 23 | 24 | 26 | 27 | 28 | 30 | 31 | 32 | 34 | 35 | 36 | 38 | 39 | 40 | 102% | 100% | Days | 133 | time axis 2005-10-18 to 2007-07-16
1 | Mobilize | 1000 | 2005-10-18 | 2005-10-18 | 4 | [163 empty] | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | bar: 2005-10-18
2 | Clear Site | 5500 | 2005-10-22 | 2005-10-22 | 4 | [164 empty] | 0 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | bar: 2005-10-22
3 | Set Stakes | 1600 | 2005-10-26 | 2005-10-26 | 4 | [164 empty] | 0 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | bar: 2005-10-26
4 | Dig Foundations | 12000 | 2005-10-26 | 2005-10-30 | 8 | [164 empty] | 0 | 6000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | bar: 2005-10-26 to 2005-10-30
5 | Clean up | 1000 | 2005-11-03 | 2005-11-03 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | bar: 2005-11-03
6 | Set Forms | 4800 | 2005-11-03 | 2005-11-03 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | bar: 2005-11-03
7 | Place Rebars | 12000 | 2005-11-03 | 2005-11-07 | 8 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 6000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | bar: 2005-11-03 to 2005-11-07
8 | Place Footings | 23000 | 2005-11-07 | 2005-11-23 | 20 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 9200 | 13800 | 18400 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | bar: 2005-11-07 to 2005-11-23
9 | Place Slab | 34000 | 2005-11-15 | 2005-11-23 | 12 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 11333.3333 | 22666.6667 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | bar: 2005-11-15 to 2005-11-23
10 | Strip Forns | 3400 | 2005-11-27 | 2005-11-27 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | bar: 2005-11-27
11 | Clean up | 1000 | 2005-11-27 | 2005-11-27 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | bar: 2005-11-27
12 | Deliver Dry Wall | 12000 | 2005-12-09 | 2005-12-09 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | bar: 2005-12-09
13 | Frame Bldg | 30000 | 2005-12-05 | 2006-01-14 | 44 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727.2727 | 8181.8182 | 10909.0909 | 13636.3636 | 19090.9091 | 21818.1818 | 24545.4545 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | bar: 2005-12-05 to 2006-01-14
14 | Install Drywall | 15000 | 2005-12-13 | 2006-01-26 | 28 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142.8571 | 4285.7143 | 4285.7143 | 6428.5714 | 8571.4286 | 8571.4286 | 10714.2857 | 12857.1429 | 12857.1429 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | bar: 2005-12-13 to 2005-12-17; 2005-12-29 to 2006-01-02; 2006-01-14 to 2006-01-18; 2006-01-26
15 | Tape Drywall | 6500 | 2006-01-18 | 2006-02-03 | 16 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625 | 3250 | 4875 | 6500 | 6500 | 6500 | 6500 | 6500 | bar: 2006-01-18 to 2006-01-22; 2006-01-30 to 2006-02-03
16 | Roof | 3400 | 2006-01-18 | 2006-02-07 | 24 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566.6667 | 1133.3333 | 2266.6667 | 2833.3333 | 3400 | 3400 | 3400 | 3400 | bar: 2006-01-18 to 2006-02-07
17 | Gutters | 4000 | 2006-02-11 | 2006-02-11 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | bar: 2006-02-11
18 | Doors & Windows | 9000 | 2005-12-09 | 2006-01-06 | 16 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 6750 | 6750 | 6750 | 6750 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | bar: 2005-12-09 to 2005-12-17; 2006-01-06
19 | Painting | 9700 | 2006-01-06 | 2006-02-19 | 24 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616.6667 | 1616.6667 | 1616.6667 | 1616.6667 | 1616.6667 | 3233.3333 | 4850 | 8083.3333 | 9700 | 9700 | bar: 2006-01-06; 2006-02-03 to 2006-02-19
20 | Clean up | 2000 | 2006-02-23 | 2006-02-23 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | bar: 2006-02-23
21 | Demobilize | 2000 | 2006-02-27 | 2006-02-27 | 4 | H | [160 empty] | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | bar: 2006-02-27
22 | [5 empty] | H | [160 empty] | H
23 | [5 empty] | H | [160 empty] | H
24 | [5 empty] | H | [160 empty] | H
25 | [5 empty] | H | [160 empty] | H
26 | [5 empty] | H | [160 empty] | H
27 | [5 empty] | H | [160 empty] | H
28 | [5 empty] | H | [160 empty] | H
29 | [5 empty] | H | [160 empty] | H
30 | [5 empty] | H | [160 empty] | H
31 | [5 empty] | H | [160 empty] | H
32 | [5 empty] | H | [160 empty] | H
33 | [5 empty] | H | [160 empty] | H
34 | [5 empty] | H | [160 empty] | H
35 | [5 empty] | H | [160 empty] | H
36 | [5 empty] | H | [160 empty] | H
37 | [5 empty] | H | [160 empty] | H
38 | [5 empty] | H | [160 empty] | H
39 | [5 empty] | H | [160 empty] | H
40 | [5 empty] | H | [160 empty] | H
41 | [5 empty] | H | [160 empty] | H
42 | [5 empty] | H | [160 empty] | H
43 | [5 empty] | H | [160 empty] | H
44 | [5 empty] | H | [160 empty] | H
45 | [5 empty] | H | [160 empty] | H
46 | [5 empty] | H | [160 empty] | H
47 | [5 empty] | H | [160 empty] | H
48 | [5 empty] | H | [160 empty] | H
49 | [5 empty] | H | [160 empty] | H
50 | [5 empty] | H | [160 empty] | H
51 | [5 empty] | H | [160 empty] | H
52 | [5 empty] | H | [160 empty] | H
53 | [5 empty] | H | [160 empty] | H
54 | [5 empty] | H | [160 empty] | H
55 | [5 empty] | H | [160 empty] | H
56 | [5 empty] | H | [160 empty] | H
57 | [5 empty] | H | [160 empty] | H
58 | [5 empty] | H | [160 empty] | H
59 | [5 empty] | H | [160 empty] | H
60 | [5 empty] | H | [160 empty] | H
61 | [5 empty] | H | [160 empty] | H
62 | [5 empty] | H | [160 empty] | H
63 | [5 empty] | H | [160 empty] | H
64 | [5 empty] | H | [160 empty] | H
65 | [5 empty] | H | [160 empty] | H
66 | [5 empty] | H | [160 empty] | H
67 | [5 empty] | H | [160 empty] | H
68 | [5 empty] | H | [160 empty] | H
69 | [5 empty] | H | [160 empty] | H
70 | [5 empty] | H | [160 empty] | H
71 | [5 empty] | H | [160 empty] | H
72 | [5 empty] | H | [160 empty] | H
73 | [5 empty] | H | [160 empty] | H
74 | [5 empty] | H | [160 empty] | H
75 | [5 empty] | H | [160 empty] | H
76 | [5 empty] | H | [160 empty] | H
77 | [5 empty] | H | [160 empty] | H
78 | [5 empty] | H | [160 empty] | H
79 | [5 empty] | H | [160 empty] | H
80 | [5 empty] | H | [160 empty] | H
81 | [5 empty] | H | [160 empty] | H
82 | [5 empty] | H | [160 empty] | H
83 | [5 empty] | H | [160 empty] | H
84 | [5 empty] | H | [160 empty] | H
85 | [5 empty] | H | [160 empty] | H
86 | [5 empty] | H | [160 empty] | H
87 | [5 empty] | H | [160 empty] | H
88 | [5 empty] | H | [160 empty] | H
89 | [5 empty] | H | [160 empty] | H
90 | [5 empty] | H | [160 empty] | H
91 | [5 empty] | H | [160 empty] | H
92 | [5 empty] | H | [160 empty] | H
93 | [5 empty] | H | [160 empty] | H
94 | [5 empty] | H | [160 empty] | H
95 | [5 empty] | H | [160 empty] | H
96 | [5 empty] | H | [160 empty] | H
97 | [5 empty] | H | [160 empty] | H
98 | [5 empty] | H | [160 empty] | H
99 | [5 empty] | H | [160 empty] | H
100 | [5 empty] | H | [160 empty] | H
|  | 192900 | 2005-10-18 | 2006-02-27 | <=133 Days | [163 empty] | 0% | 0% | 7.309% | 10.42% | 16.54% | 24.42% | 32.68% | 40.94% | 51.48% | 51.48% | 52.89% | 65.38% | 69.07% | 70.49% | 74.43% | 76.95% | 80.37% | 84.31% | 86.56% | 87.69% | 90.23% | 92.21% | 93.34% | 97.09% | 97.93% | 100%
| Nothing below here | Hide Rows with "H" showing in Col. G. |  |  |  |  | 2005-10-18: Nothing below here; 2005-11-27: Hide Cols with "H" showing in Row 1.; 2006-02-27: Nothing below here |  | Formulas only to right. No User entry!
Note on FN5: Cell[HB5] Formula: 0
Note on FO5: Cell[HC5] Formula: =IF($C5<>0,SUM(INDIRECT(ADDRESS(CELL("row",$H5),8) & ":" & ADDRESS(CELL("row",$H5),HC$4)))/$F5*$F$3*$C5,"")
Note on I4: Cell[I4] Formula: =H4+Intv