## WWMNTHLY
|  | Low Bid | Project Mgr. | Scheduled or Actual Dates |  |  |  | % Compl. | WA | Remarks | Final Report for Construction | Date Record Drawings
Sup. | Project Name | or | Design Eng. | Plan | Contract | Const. | Const. | Design/ | Auth/
Dist. | Project Number | Estimate | Contractor | Approval | Award | Start | Comp. | Const. | Balance
4 | District No. 1 MWTP Office/Laboratory Building & Remodel Exist. Lab Facility WS232827 | $1,650,000 | S. Pan, Leach Mounce Arch. | 12/13 | 03/14 | 04/14 | 02/15 | 40/0 |  | Negotiated a Consulting Services Contract. AE Contract approved by the Board on 3/26/13. Completed schematic design of building floor plan, elevation views, site plan, site survey, and Geotechnical Investigation.
4 | District No. 1 Stockton Reservoir WS231803 | $750,000 | S. Pan, Penfield & Smith | 12/13 | 03/14 | 04/14 | 04/15 | 0/0 |  | Completed Preliminary Design Report (PDR). Next step is to prepare a geotechnical report for the preferred reservoir site.
4 | District No. 1 Roseland Booster Pump Station WS231886 | 562242 | Keller WREA Blois | 04/09 | 08/05/09 | 09/02/09 | 10/4/10 | 100/100 |  | Release on Contract received 11/03/10 from Blois. NOC recorded 11/19/10, with final payment in 12/10. | 2012-04-11
4 | District No. 1 Reclaimed Water Dist. Sys Phase II WS232828 | 1576177 | Keller/Martinez Kennedy/Jenks Padre Assoc. M.Muna Canyon Springs Ent. | 09/10 | 01/11 | 02/8/11 | 07/24/12 | 100/100 |  | Bids opened on 11/23/10. Project awarded by BOS on 1/11/11. Pre Construction meeting held on 2/3/11. NTP issued 4/6/11. Tank is complete. Tank site work is completed and Recycled Water Pipeline on Hitch Blvd. is complete with the exception of reinstalling chain link fencing. Final inspection conducted 7/24/2012. NOC Recorded 9/14/2012. Kennedy Jenks submitted final As Builts for review. | 2012-09-27
4 | District No. 1 MWTP Desalter Project WS231801 | $48,000,000 | S. Pan, Kennedy Jenks, Hopkins Groundwater Consulting, Dr. Steven Bachman ESA Associates | 03/15 | 06/15 | 07/15 | 12/16 | 0/0 |  | Completed Preliminary Design Report in 2010. Completed Preliminary Pilot study in February 2012. Completed ground water model in June 2013. Next step is to conduct additional geotechnical investigation and pilot well study, prepare an EIR, and to obtain CDPH and Fox Canyon GMA approval.
4 | District No. 1 Recycled Water System - Phase IV WS232829 | $4,200,000 | S. Pan, Penfield & Smith, Padre & Assoc. | 08/14 | 11/14 | 12/14 | 12/15 | 0/0 |  | Submitted Prop. 84 grant application to Watershed Coalition of Ventura County. Completed CEQA initial study in July, 2013 and to be submitted to State Clearinghouse for public review in August, 2013. Preliminary Design Report (PDR) is underway by Penfield & Smith.
4 | District No. 16 Piru WTP Phase II-Tertiary Treatment Facility Project WS236704 | 2000000 | S. Pan | 03/14 | 05/14 | 06/14 | 06/15 | 0/0 |  | BOS approved Tetra Tech design services contract in August, 2013. Norman's Nursery indicated intrest in using recycled water from Piru WWTP.
2 | District No. 17 Bell Canyon High Pressure Pipeline from Hacienda Road to Dapplegray Road WS237893 | 800000 | S. Pan BTC Labs - Vertical 5 | 09/13 | 12/13 | 01/14 | 06/14 | 0/0 |  | Issued AE Contract on 2/28/13 with revised scope of work. Consultant completed draft technical memo. District reviewed and commented on the Tech. Memo. Consultant is finalizing the Tech Memo.
2 | District No. 19 Well No. 2 Iron and Manganese facility WS239898 | 900000 | S. Pan RBF Consulting Padre & Assoc, Inc. | 04/14 | 07/14 | 08/14 | 08/15 | 99/0 |  | Seeking USDA Funding. Engineering and Environmental reports submitted to USDA 10/25/11. Work order to RBF issued 1/26/12 to finalize the design. RBF submitted final Plans and Specs., on 10/25/12. Construction phase Engineering Services Contract is issued.
2 | District No. 19 Balcom Canyon Turnout WS239901 | $330,000 | Eric Keller CMWD Phoenix Eng., Inc. Northwest Hydraulics, Inc | 08/13 | 10/13 | 11/13 | 06/14 | 50/0 |  | Calleguas' Consultant, Phoenix Engineering, inc. has completed the Preliminary Design Report (PDR), and Northwest Hydraulics is performing the surge analysis.
2 | District No. 19 Sand Canyon Rd. Booster Pump Station WS239902 | 300000 | S. Pan Padre & Assoc, Inc. BTC Labs - Vertical V | 07/13 | 11/13 | 12/13 | 12/14 | 100/0 |  | Seeking USDA Funding. Engineering and Environmental reports submitted to USDA 10/25/11. Completed bid documents and project package. Construction contract advertised in Aug. 2013, bid open in Sept. 2013.
2 | District No. 19 Pipe Replacement @ County Roads R/W WS239903 | 1500000 | S. Pan Padre & Assoc, Inc. Phoenix Engineering, Inc. | 08/13 | 11/13 | 12/13 | 09/14 | 97/0 |  | Seeking USDA Funding. Engineering and Environmental reports submitted to USDA 10/25/11. Phoenix Engineering completed 100% Plans and Specs. Next step is to complete bid documents and project package.
2 | District No. 19 Pipe Replacement @ CalTrans R/W WS239904 | 1300000 | S. Pan Padre & Assoc, Inc. AECOM Technical Services, Inc. | 05/14 | 08/14 | 09/14 | 09/15 | 99/0 |  | Seeking USDA Funding. Engineering and Environmental reports submitted to USDA 10/25/11. AECOM submitted 90% plans to all review Agencies including Cal Trans, Calleguas MWD, VCWPD, and WWD#19.
5 | El Rio Sewer Project - Phase 5B, 5C, & 5D WS228236 | 7076400 | Munoz/Segui Penfield & Smith Specialty Const. Inc | 06/09 | 2009-10-20 | 2009-11-17 | 04/11/11 | 100/100 |  | Bids were opened on 8/18/09. Project was awarded 10/20/09. Pre-construction and community meeting with residents held 11/5/09. Meeting with 5C & D residents held May 6, 2010. Taking beneficial use of phase 5B on July 1, 2010. Meeting with 5B residents held 6/24/10 to connect. Meeting with 5C & D residents held 2/24/11 to connect. Final inspection conducted 4/19/11. Notice of Completion recorded 7/15/11. Final payment 8/02/11. | 03/12/12
5 | El Rio Sewer Project - Prop. 50 - Phase 7A WS228235 | 1108374 | Munoz Penfield & Smith Fugro West, Inc. Camarillo Engineering | 08/08 | 10/13/08 | 12/8/08 | 05/29/09 | 100/100 |  | Board approved change order 10/07/08. Public meeting held on 12/4/08. The Final Inspection was performed on 6/2/09. Residents have started connecting their laterals to the sewer system. One year warranty inspection conducted 5/25/10. Final payment 5/10/10. | 03/23/12